## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Graphics cause include issues with SDK | 40 | 13 | 520 | 2021-10-29 | 2021-11-05 | R | Unit testing for LCD proved that polygon function for LCD is working
Segger malfunctions again (RTT block gets address 0 always) | 13 | 8 | 104 | 2021-10-29 | 2021-10-29 | M | Will use roomates laptop for Segger analysis if needed. Belief is my SDK install has issues that the other laptop does not.
Dev Kit breaks | 2 | 20 | 40 | 2021-10-29 |  | A | Get replacement from friend if necessary
Unknown how long physcis engine development will take | 13 | 5 | 65 | 2021-10-29 |  | O | No update yet, still worried about the unkowns of the physics
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100